## Product Catalog
Project Name | LockedMe.com
StakeHolders/Customers/Users | abc/xyz/zxc etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
For a new LockedMe.com website to launch, the highest business value will be when a new user is able to Login and keep the Files safe into the website. (DealMart_Epic_001) | US001 | As a user,I want to Register to the application with a username and password. | As a first-time user ,Go to registration page,enter the valid credentials and promot out the succeccful welcome message . | New
| US002 | As a Registered user,Iwant to login with my credentials | As a registered user, I want to Login with username and password which I have enterted at the time of registration and navigate to main menu of my application. | New
| US003 | As a Registered User can see the Files listed. | As a register user, I want to able to browse the files in the list as an alphabetical order, so that I can have choice of choosing the correct file to retrieveSo that I can make my choice and buy a listed product from the website. | New
| US004 | Registered User can add ,search and delete files from the application. | As a Registered User, I want to be able to add ,delete and search files in the website. | New
| US005 | Registered User has to navigate. | As a registered user, after completing the above tasks, user has to navigate and return to main menu and exit . | New

## Sprint Planning
Project Name | LockedMe.com
Scrum Team | Dev, QA, PO, Scrum Master etc.
Created By | Product Owner
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprint
For a new LockedMe.com website to launch, the highest business value will be when a new user is able to Login and keep the Files safe into the website. (DealMart_Epic_001) | US001 | As a user,I want to Register to the application with a username and password. | As a first-time user ,Go to registration page,enter the valid credentials and promot out the succeccful welcome message . | 8 | 1
| US002 | As a Registered user,Iwant to login with my credentials | As a registered user, I want to Login with username and password which I have enterted at the time of registration and navigate to main menu of my application. | 3 | 1
| US003 | As a Registered User can see the Files listed. | As a register user, I want to able to browse the files in the list as an alphabetical order, so that I can have choice of choosing the correct file to retrieveSo that I can make my choice and buy a listed product from the website. | 5 | 2
| US004 | Registered User can add ,search and delete files from the application. | As a Registered User, I want to be able to add ,delete and search files in the website. | 5 | 3
| US005 | Registered User has to navigate. | As a registered user, after completing the above tasks, user has to navigate and return to main menu and exit . | 8 | 3